## Slide 1: Quality Check of Engineering Documents
Vinit Dave
Sindhuja Reddy
Li Guan
Sujan Gaha Magar
Madeline Goldy
Group 2
Project Plan – Ingenia

## Slide 2: Agenda
Project Background and Description
Project Scope
Risks
Budget
Roles and Responsibilities
Communications Plan
Project Stakeholders
Deliverables and Project Evaluation Criteria
Implementation Plan

## Slide 3: Project Background and Description
Ingenia: Client-focused consulting company
Quality Check of Engineering Documents Initiative
Project's Organizational Importance
Project's Objectives and Benefits

## Slide 4
AS IS Process
Manual Quality Assessment
Reviewer Dependency
Limited Automation
Documentation Challenges
Collaboration Hurdles
Reporting Bottlenecks
Notes: Manual Quality Assessment:
  Core of the process; involves review of engineering deliverables (reports, drawings).
  Experts evaluate against predefined checklist, including formatting, content accuracy, and adherence to industry standards.
Reviewer Dependency:
  Process relies heavily on individual reviewers' expertise and availability.
  Variations in evaluation methods, feedback, and timelines can lead to inconsistencies.
Limited Automation:
  Basic automation for tracking and notifications.
  Manual management of reminders for incomplete assessments, leading to potential delays.
Documentation Challenges:
  Documents stored physically and in scattered digital files.
  Lack of centralized repository hampers version control and retrieval, causing inefficiencies.
Collaboration Hurdles:
  Absence of integrated collaboration tools for stakeholders.
  Marking up drawings, feedback exchange, and real-time interactions outside formal assessment.
Reporting Bottlenecks:
  Tracking progress and generating quality reports is time-consuming.
  Manual reporting methods make extracting insights challenging.

## Slide 5
TO BE Process
Digitalization of Quality Checklist
Tool Selection
Wireframe Creation
User-Centric Design
Research on Automation of Checklist Tasks
Thorough Automation Exploration
Feasibility and Applicability Analysis
In-Depth Documentation and Recommendations
Notes: 1. Digitalizing the Quality Checklist:
Tool Selection: Utilizing Figma/Online Forms for versatile design and prototyping.
Wireframe Creation: Detailed wireframes in Figma, replicating paper-based checklist structure and elements.
User-Centric Design: Prioritizing user experience with intuitive navigation and device responsiveness.
2. Automation Research for Checklist:
Thorough Automation Exploration: Investigating machine learning, NLP, and image recognition technologies.
Feasibility Analysis: Assessing automation potential for checklist items based on complexity, accuracy, and benefits.
Documentation and Recommendations: Comprehensive report with research process, outcomes, and actionable automation recommendations.

## Slide 6
Project Scope
Inclusions
User-centric digital checklist via Figma wireframes.
Exclusions
Limited automation implementation (focus on research and recommendations).
Comprehensive automation technology research with documented findings.
Recommendations & solution design documentation.
No integration of dashboard with Drawboards.
Notes: 1. Project Inclusions
• A meticulously designed digital checklist, created using Figma wireframes, fostering a user-centric and intuitive experience.
• Thorough research into automation technologies, accompanied by documented findings and recommendations/solution design document.
2. Project Exclusions
• Full-scale implementation of automation for all checklist items (limited to research and recommendations) with the working application.
• Integration of dashboard with Drawboards

## Slide 7: Risks
Risk | Probability (out of 100%) | Impact | Mitigation Strategy
Lack of technical expertise | 70% | High | Research, mentor guidance, contact clients and having regular meetings, dividing tasks based on strengths.
Misalignment with project goals | 20% | High | Regular alignment checks with mentors and clients, clear documentation of goals and requirements.
Changes in the project scope | 20% | Medium | Re-negotiating project scope, consulting with mentors.
Client’s availability | 20% | High | Reach out to a representative
Unexpected circumstances | 10% | Medium | Seek mentor advice, have a risk management plan in place
Unavailability of data | 10% | High | Identify alternate data sources, make necessary adjustment to project plan

## Slide 8: Budget
Budget Item | Estimated Cost | Justification
Software Development Resources | $25,000 | Allocation for skilled developers, UX/UI designers, and QA (Quality Assurance) testers to create the application.
Server Hosting and Maintenance | $5000 | Provisioning and maintaining servers for hosting the application, ensuring reliability and security.
Integration with Drawboard Projects | $3000 | The cost associated with integrating the app with Drawboard, expanding collaboration capabilities.
Quality Assurance and Testing | $6000 | Investment in rigorous testing to ensure the application's functionality, security, and user experience.
User Interface/Experience Enhancement | $4000 | Budget for refining the app's design, optimizing user flows, and ensuring an intuitive user experience.
Notes: The budget covers vital development resources, server hosting, quality assurance, drawboard integration, and user experience enhancements. It lays a strong groundwork for a robust and user-friendly solution aligned with Ingenia's needs.
Note: Figures are based on data from Fiverr/Upwork freelancing platforms and AWS Cloud Server Hosting.

## Slide 9
Roles & Responsibilities
Role | Student | Responsibility | Rationale
Requirements Analyst | Madeline Goldy | Collecting and analysing requirements | Strong analytical and communication skills
Documentation & Process Analyst | Sindhuja Reddy | Document all processes, findings, and strategies, ensure clarity and coherence in documentation, review and revise as necessary | Ensures thorough and coherent documentation of all processes.
Prototyping Specialist | Li Guan | UI design, proof-of-concept/mock-up with Figma | Creative mindset and experience in UI design tools
Research and Development Lead | Sujan Gaha Magar | Conduct in-depth research on OCR and digitalization, guide the team on technical aspects. | Background in engineering and research, apt for understanding OCR and digitalization.
Project Manager & Workflow Designer | Vinit Dave | Project coordination, swim lanes diagram | Leadership qualities and ability to oversee multiple aspects

## Slide 10: Communication Plans
1. Client Communication
Purpose: To update the client on project status, gather feedback, and align on expectations.
Method: Zoom call, email updates, formal reports.
Frequency: Bi-weekly meetings, monthly reports.
2. Mentor Communication
Purpose: To seek guidance, validate project direction, and ensure adherence to best practices.
Method: Zoom call, email communication, Microsoft Teams.
Frequency: weekly meetings, or as needed, weekly progress report.
3. Team Members Communication
Purpose: To ensure alignment, collaboration, task tracking, and addressing any issues.
Method: weekly team meetings, collaboration tools like Microsoft Teams, Whatsapp messaging app
Frequency: weekly for team meetings, or as needed

## Slide 11: Project Stakeholders
Stakeholder | Interest or Concerns
End User (Future Stakeholder) | Requiring a user-friendly interface, efficient functionality, and the ability to easily manage and assess engineering documents.
Software Developer (Future Stakeholder) | Providing necessary software or hardware components, meeting integration requirements, and maintaining long-term business relationships.
Client Organization Staff | Ensuring that the project meets their specific needs, aligns with their standards, and facilitates improved quality assurance for engineering deliverables.
Project Team | Meeting project goals, adhering to deadlines, ensuring personal growth and skill development, collaborating effectively.
Project Mentor | Guiding the team, sharing industry knowledge, ensuring the project meets industry standards, supporting team growth.

## Slide 12: Deliverables
1. Documentation for Digitalization
Purpose: Smooth transition from manual to digital checklists
Includes: Architectural framework, process flow, user interface and more
Empowers Ingenia to implement a user-friendly app
2. Investigation Report for Automation
Purpose: Analyse automation opportunities for checklist tasks
Focus: Information block in Engineering Drawings
Guides Ingenia's informed decisions on automation
3. Agile Project Plan
Purpose: Align project execution with goals and milestones
Features: Detailed sprint-based roadmap for efficient task management
4. Technical Prototypes
Purpose: Showcase tangible outcomes of research and development
Includes: OCR technology prototypes and user-friendly Figma prototypes
5. Integration Documentation and Strategies
Purpose: Connect innovative ideas with practical implementation
Provides a clear roadmap for integrating OCR automation and digital checklists

## Slide 13: Evaluation Criteria
1. Documentation for Digitalization
Completeness and accuracy of requirement documents
Effectiveness of Figma mock-up for user interface and experience
2. Investigation of Automation Opportunities
Thoroughness of the investigation report
Clarity in identifying suitable checklist tasks for automation
3. Agile Implementation and Progress
Adherence to bi-weekly sprint structure
Demonstrated progress and alignment with project goals
4. Technical Prototypes
Functionality and accuracy of OCR technology prototypes
Quality of Figma prototypes representing digital checklists
5. Integration Documentation and Strategies
Clarity and effectiveness of integration strategies

## Slide 14: Project Implementation
Initial Research and Planning
In-depth Research on OCR and Checklist Digitalization
Exploring OCR and Digitalization Opportunities
Formulating Strategies for OCR and Digitalization
Prototyping OCR and Digitalization
Refining Strategies and Documentation
Presentation and Conclusion

## Slide 15
THANK YOU!!